## Аркуш1
Project Description:
B2C website for Skybot company engaged in the retail and maintenance of electric vehicles
Introduction
Step | Status
Initial discussions with the client to establish expectations and requirements
Establish entry criteria based on the agreed requirements
Start MVP development and testing
Entry Criteria:
Prerequisites: established requirements, testing team assembled, testing enviroment set up
Process | Description | Priority | Test cases | Status | Expected result | Actual result
1. Webhosting | quick, stable, and safe webhosting, able to withstand high amount of users with an uptime of 99% | 2 |  |  | developed, tested and implemented
2. Mobile version | mobile version optimised for mobile devices | 10 |  |  | developed, tested and implemented
3. Design | userfriendly and intuitive with CMS | 9 |  |  | developed, tested and implemented
4. Order funcionality | quick process of ordering items | 1 |  |  | developed, tested and implemented
5. Account | option to create user accounts | 4
6. User safety | secure user information and payment | 3 |  |  | developed, tested and implemented
7. Item descriptions | information about items sold with detailed description | 11 |  |  | developed, tested and implemented
8. Test-drive sign up | process of signing up for a test-drive | 6 |  |  | developed, tested and implemented
9. Maintenance sign up | process of setting up an appointment for service | 5 |  |  | developed, tested and implemented
10. Reviews | rating & comment functionality with option to attach media files | 8 |  |  | developed, tested and implemented
11. Individual recomendations | personalized recommendations for users and notifications about ongoing promotions | 12 |  |  | developed, tested and implemented
12. Videohosting integration | videohosting integration to view reviews of the items | 7 |  |  | developed, tested and implemented
13. Analytics toolset | seo-toolset integration | 13 |  |  | developed, tested and implemented
Tests to be Performed
Functional testing
Perfomance testing
Payment gateway testing
Security testing
UI testing
Usability testing
Accesability testing
Smoke testing
Regression testing
Test Deliverables
Test | Description | Status | Expected result | Actual result | Comment
Check-lists, test cases, bug reports, fixes, etc
Environmental tests
Client Side
System | Browser | Status | Expected result | Actual result | Comment
Windows 10/11 | Google Chrome |  | Application runs in stable manner.
| Microsoft Edge |  | Application runs in stable manner.
| Mozilla Firefox |  | Application runs in stable manner.
ubuntu 20+ | Google Chrome |  | Application runs in stable manner.
| Microsoft Edge |  | Application runs in stable manner.
| Mozilla Firefox |  | Application runs in stable manner.
MacOS Monterey | Google Chrome |  | Application runs in stable manner.
| Microsoft Edge |  | Application runs in stable manner.
| Mozilla Firefox |  | Application runs in stable manner.
| Safari |  | Application runs in stable manner.
Android 11+ | Google Chrome |  | Application runs in stable manner. |  |  | android 11 is the oldest version with security support
| Microsoft Edge |  | Application runs in stable manner.
| Mozilla Firefox |  | Application runs in stable manner.
iOS 17 | Google Chrome |  | Application runs in stable manner.
| Microsoft Edge |  | Application runs in stable manner.
| Mozilla Firefox |  | Application runs in stable manner.
| Safari |  | Application runs in stable manner.
Server Side
System | Status | Expected result |  | Actual result | Comment
4 vCPU Cores |  | Application runs in stable manner.
16 GB RAM
200 GB NVMe Disk space
4 TB Bandwidth
1 Snapshot
Weekly Backups
Dedicated IP Address
Full Root Access
AI Assistant
Exit Criteria
agreed release date
all test cases completed
no severe bugs found for last 2 weeks
all known bugs fixed
project manager's expectations met
client's expectations met
Risks and Contingencies
Risk | Description | Contingency
Technical issues | possible crashes, slow performance, or compatibility problems | conduct testing procedures to identify and fix any technical, provide regular updates and bug fixes, address user-reported problem
Design issues | possible customer confusion due to UI/UX complexities | conduct UI, usability, and accessibility testing to cover as many possible use-cases as possible
Security weaknesses | possible data leaks, backdoors, backup corruption, etc | provide encryption protocols, secure authentication, conduct regular security audits to safeguard user data, respond quickly to breaches
Payment issues | possible failed transactions, double charges, or inaccurate billing | provide reliable and secure payment options, establish ways for users to report payment-related problems to customer service
Client's change of expectations | possible changes to requirements due to change of client's opinions or miscommunication | establish a clear conversation with the client, keep them updated on project's development
staffing issues | some personnel may be unavailable or join the project with a delay | establish a robust network and development plan
hardware/devices issues | possible unavailability of hardware/devices required for development and testing | establish clear hardware/devices requirements for development and testing